## ProjectData
Column | Project_Name | Location | Budget | Actual_Cost | Planned_Days | Actual_Days | Open_Risks | Risk_Level | Cost_Variance | Cost_Variance_% | Delay Days
P001 | Vienna Office Tower | Vienna | 500000 | 560000 | 180 | 205 | 5 | High | 60000 | 12% | 25
P002 | Graz Housing Complex | Graz | 350000 | 340000 | 150 | 148 | 1 | Low | -10000 | -2.857% | -2
P003 | Linz Bridge Project | Linz | 800000 | 890000 | 240 | 275 | 6 | High | 90000 | 11.25% | 35
P004 | Salzburg Renovation | Salzburg | 250000 | 265000 | 120 | 130 | 3 | Medium | 15000 | 6% | 10
P005 | Innsbruck Office | Innsbruck | 420000 | 415000 | 160 | 158 | 1 | Low | -5000 | -1.19% | -2
P006 | Vienna Metro Extension | Vienna | 950000 | 1080000 | 300 | 340 | 7 | High | 130000 | 13.68% | 40
P007 | Graz School Building | Graz | 380000 | 395000 | 170 | 178 | 3 | Medium | 15000 | 3.947% | 8
P008 | Linz Industrial Hall | Linz | 600000 | 590000 | 210 | 205 | 2 | Low | -10000 | -1.667% | -5
P009 | Salzburg Hotel | Salzburg | 720000 | 780000 | 220 | 242 | 5 | High | 60000 | 8.333% | 22
P010 | Vienna Residential Block | Vienna | 450000 | 470000 | 180 | 190 | 3 | Medium | 20000 | 4.444% | 10
P011 | Innsbruck Warehouse | Innsbruck | 310000 | 305000 | 140 | 138 | 1 | Low | -5000 | -1.613% | -2
P012 | Graz Shopping Centre | Graz | 680000 | 750000 | 230 | 255 | 5 | High | 70000 | 10.29% | 25
P013 | Vienna Hospital Wing | Vienna | 870000 | 910000 | 270 | 285 | 4 | Medium | 40000 | 4.598% | 15
P014 | Linz Apartment Complex | Linz | 540000 | 530000 | 190 | 188 | 2 | Low | -10000 | -1.852% | -2
P015 | Salzburg Office Park | Salzburg | 610000 | 650000 | 200 | 215 | 4 | Medium | 40000 | 6.557% | 15
P016 | Vienna Logistics Centre | Vienna | 760000 | 850000 | 250 | 280 | 6 | High | 90000 | 11.84% | 30
P017 | Graz Sports Centre | Graz | 490000 | 500000 | 175 | 180 | 2 | Medium | 10000 | 2.041% | 5
P018 | Innsbruck Student Housing | Innsbruck | 400000 | 390000 | 165 | 160 | 1 | Low | -10000 | -2.5% | -5
P019 | Linz Research Centre | Linz | 700000 | 760000 | 225 | 245 | 5 | High | 60000 | 8.571% | 20
P020 | Vienna Retail Complex | Vienna | 580000 | 600000 | 195 | 202 | 3 | Medium | 20000 | 3.448% | 7